## Sheet1
Task | Assigned To | Start Date | End Date | Status | Notes | Done?
Set up repository and file structure | Urvi | 2025-11-13 | 2025-11-14 | In Progress
Design UI mockups | Worker 2 | 2025-11-14 | 2025-11-16 | Not Started
Frontend: Component scaffolding | Worker 3 | 2025-11-15 | 2025-11-18 | Not Started
Backend: API skeleton | Worker 4 | 2025-11-15 | 2025-11-18 | Not Started
Database setup | Worker 4 | 2025-11-15 | 2025-11-17 | Not Started
Integrate user auth | Worker 1 | 2025-11-17 | 2025-11-19 | Not Started
Frontend: Dashboard styling | Worker 2 | 2025-11-18 | 2025-11-21 | Not Started
Course pages logic & UI | Worker 3 | 2025-11-19 | 2025-11-22 | Not Started
Backend: Course APIs | Worker 4 | 2025-11-19 | 2025-11-22 | Not Started
Add calendar/reminder features | Worker 1 | 2025-11-20 | 2025-11-23 | Not Started
Student and vendor profile pages | Worker 2 | 2025-11-21 | 2025-11-24 | Not Started
Connect frontend/backend | Worker 3 | 2025-11-22 | 2025-11-25 | Not Started
Testing (unit/integration) | Worker 4 | 2025-11-23 | 2025-11-27 | Not Started
Fix UI/UX bugs & polish | Worker 2 | 2025-11-24 | 2025-11-27 | Not Started
Deploy to staging | Worker 1 | 2025-11-27 | 2025-11-28 | Not Started
Final presentation/documents | Worker 3 | 2025-11-28 | 2025-11-28 | Not Started